| Id | Activity Type | Starting Period | Description |
| --- | --- | --- | --- |
| P1 | Other Project Events | 09-2019 | Project team will be created in each partner school. All partner schools will announce the results to the teachers, parents, relevant stakeholders, students and local press at the meeting of their own school. |
| P2 | Other Project Events | 10-2019 | Online webinar/Skype or eTwinning meeting with contact persons. Students to attend the Spanish meeting will meet their Spanish peers via eTwinning.net platform. Each school prepare a PPT presentation on plant diversity in their own country and they will take it to Spain meeting. |
| C1 | Short-term exchanges of groups of pupils | 11-2019 | Diversity of Plants |
| P3 | Other Project Events | 11-2019 | Participants in the Spain meeting will answer the online evaluation and satisfaction questionnaire. |
| P4 | Other Project Events | 12-2019 | Each partner school will share the Spain meeting activities and results in the project and school website, social media, Twin Space and blog. |
| P5 | Other Project Events | 01-2020 | All partners will prepare the project banner and corner at school. |
| P6 | Other Project Events | 02-2020 | Teaching students to prepare online posters at partner schools. |
| P7 | Other Project Events | 03-2020 | The students of the partner schools will research sea or river biodiversity in their own region. |
| P8 | Other Project Events | 04-2020 | Each school will prepare a PPT presentation of sea or river biodiversity in their own region and they will take it to France meeting. |
| C2 | Short-term exchanges of groups of pupils | 05-2020 | Diversity in water |
| P9 | Other Project Events | 05-2020 | Celebrating International Biodiversity Day at partner schools. (22 May) |
| P10 | Other Project Events | 06-2020 | Each partner school will share the France meeting activities and results in the project and school website, social media, Twin Space and blog. Coordinator meeting on Skype or webinar to evaluate the 1st year of the project. Participants in the France meeting will answer the online evaluation and satisfaction questionnaire. |
| P11 | Other Project Events | 07-2020 | All coordinators will write the progress report of the |

project.

| P12 | Other Project Events | 08-2020 | All coordinators will write the progress report of the project and send it to their own National Agency. |
| --- | --- | --- | --- |
| P13 | Other Project Events | 09-2020 | The students of partner schools will research the livings that are about to become extinct in their own countries and prepare a PPTpresentation for the Turkey meeting. Partner schools will review the time table. Coordinators meeting on Skype for progress. |
| C3 | Short-term exchanges of groups of pupils | 10-2020 | Endangered species |
| P14 | Other Project Events | 10-2020 | Participants in the Turkey meeting will answer the online evaluation and satisfaction questionnaire. |
| P15 | Other Project Events | 11-2020 | Each partner school will share the Turkey meeting activities and results in the project and school website, social media, Twin Space and blog. |
| P16 | Other Project Events | 12-2020 | Preparing “Nature's Superheroes” Biodiversity Comic Book at partner schools. |
| P17 | Other Project Events | 01-2021 | One of the project manager will organize an online seminar about different practices that can be included in science curriculum on e-Twinning. |
| C4 | Short-term exchanges of groups of pupils | 02-2021 | Animal and Insect Diversity |
| P18 | Other Project Events | 02-2021 | The students will research animal/insect diversity of their own countries, prepare a PPT presentation and take it to Bulgaria meeting. |
| P19 | Other Project Events | 03-2021 | Each partner school will share the Bulgaria meeting activities and results in the project and school website, social media, Twin Space and blog. Participants in the Bulgaria meeting will answer the online evaluation and satisfaction questionnaire. Annual Photography Competition. |
| P20 | Other Project Events | 04-2021 | Each school will be organised a biodiversity campaigne in local. The students and personnel will send SMS with slogan and multimedia to all people on their phone list and reach more people. |
| C5 | Short-term exchanges of groups of pupils | 05-2021 | Ecosystem diversity |
| P21 | Other Project Events | 05-2021 | The students of partner schools will research ecosystems and prepare PPT presentation for the |

meeting in Czech R.

| P22 | Other Project Events | 06-2021 | Each partner school will share the Czech Republic meeting activities and results in the project and school website, social media, Twin Space and blog. Coordinator meeting on Skype or webinar to evaluate the 1nd year of the project. Participants in the Czech Republic meeting will answer the online evaluation and satisfaction questionnaire. |
| --- | --- | --- | --- |
| P23 | Other Project Events | 07-2021 | The project coordinator will upload the results with their links into the Erasmus+ Results Platform. |
| P24 | Other Project Events | 08-2021 | All project managers will write the final report and submit it on Mobility Tool. |